CIWMB Pharmaceuticals Waste Management Plan to Implement SB 966

Vision

The vision for the CIWMB‘s activities related to pharmaceuticals, and where feasible, sharps, is to provide local jurisdictions in California with the tools to implement collection programs as well as work with manufacturers, retailers, pharmacies, hospitals and other health-related constituents, which allow for the proper disposition of pharmaceuticals and sharps in a single location.

Goal for Pharmaceutical Collection

The goal of the CIWMB pharmaceutical activities is to develop model programs for rural and urban areas that meet established statutory criteria for the collection of unused and expired pharmaceuticals.

Working with External Stakeholders

By working with external stakeholders to review established statutory criteria and other essential elements for pharmaceutical collection program, CIWMB will be better able to craft a model program that will fit the needs of California residents.  The CIWMB has already established the Pharmaceutical Working Group (Working Group) consisting of staff from the California Department of Public Health, the Board of Pharmacy, the Department of Toxic Substances Control, and the State Water Resources Control Board.  On a national and regional level, the CIWMB is also working with the Product Stewardship Institute National Dialogue and the California Product Stewardship Council.

Information Gathering

The CIWMB will identify programs that meet statutory criteria by surveying in late June 2008 existing programs in California, other states,  and abroad.  Survey results will be summarized and analyzed as to program efficiency, public convenience, cost-effectiveness, sustainability, environmental effectiveness, and efficacy for different populations and population densities. Information from the survey will be incorporated into staff recommendations for model collection program criteria.  Survey results will be available in late August 2008.

The CIWMB will review, summarize and evaluate other states’ and governmental entities’ pharmaceutical collection programs.  In addition, CIWMB will determine which programs meet the criteria set forth in Senate Bill 966.

Information Dissemination to Interested Parties

The CIWMB is developing a Pharmaceuticals Web Page to contain lists of collection programs with a short program description, a searchable collection data base, resources, and links to laws and regulations.  The initial version of this Web Page can be accessed at http://www.ciwmb.ca.gov/HHW/PharmWaste/

A follow-up Stakeholders’ Meeting is planned for August 25, 2008 to survey and review the first iteration of ideas for Model Programs.  Staff will post survey results on the CIWMB’s Pharmaceuticals Web Page around that time.  Staff will finalize the description, criteria, and essential elements for model programs and present this information to the CIWMB Board in Fall 2008 summarizing the survey results and staff recommendations for model collection programs.

Develop Model Program Criteria

A description of the model programs along with the established criteria for model collection programs will be made available on the Pharmaceutical Web Page  as guidance documents for pharmacies and businesses interested in collecting and disposing of pharmaceuticals. Collection programs may differ between rural and urban areas.  CIWMB staff will track collection program locations and collection data to evaluate amounts and types of pharmaceuticals diverted from waste streams, thus evaluating the effectiveness of the model program criteria.

Report Preparation

In preparation for a Report to the Legislature due December 2010, CIWMB staff will monitor collection programs during 2009 and 2010 and summarize data such as cost, amounts collected, safety issues, types of populations served, and convenience to the public.  A draft report will be presented to the CIWMB Board in late Summer 2010 for public vetting prior to submittal to the Legislature.  The Final Report will include program evaluation and recommendations for a statewide pharmaceutical collection program and any potential statutory changes that are needed.